## Budget
Job Cost Budget | [8 empty] | Landscape · one page wide
One row per cost code. Enter the original budget, approved changes, commitments and actual cost; projected final, variance and % spent calculate.
Amber cells are yours to fill in. Everything else calculates.
PROJECT | [5 empty] | CONTRACT VALUE
Project name | [5 empty] | Original contract |  |  | Revised contract
Project number | [5 empty] | Approved change orders |  |  | Projected gross profit
As of / costs through | [8 empty] | Projected margin
Prepared by | [8 empty] | Margin at bid
CODE | COST CODE DESCRIPTION | TYPE | ORIGINAL BUDGET | APPROVED CHANGES | REVISED BUDGET | COMMITTED | ACTUAL TO DATE | EST. TO COMPLETE | PROJECTED FINAL | VARIANCE | % SPENT
Totals
Type: L labor · M material · E equipment · S subcontract · O other. Projected final = actual + estimate to complete when you enter one, otherwise the larger of revised budget, committed and actual. Variance = revised budget − projected final (positive is favorable, red is over). Committed = purchase orders and subcontracts issued, invoiced or not.
Free template by BuildWorkPro — buildworkpro.com/templates. Update actual costs weekly from payroll and vendor invoices; a budget reviewed monthly is a history, not a control.

## Cost Codes
Cost Codes
A CSI MasterFormat-style starter list for a mechanical / plumbing sub. Edit freely — the codes are yours; the point is to use the same ones on every job.
Amber cells are yours to fill in. Everything else calculates.
CODE | DESCRIPTION | TYPE | NOTES
01-1000 | Supervision & project management | L
01-3000 | Submittals, coordination & closeout | O
01-5000 | Lifts, tools & temporary facilities | E
01-5400 | Crane & rigging | E
01-5600 | Vehicles & fuel | E
01-7000 | Permits, fees & inspections | O
01-8000 | Bonds & insurance | O
01-9000 | Contingency | O
01-9100 | Sales & use tax on materials | O
02-4000 | Demolition & removal | S
03-3000 | Concrete — pads, curbs & patching | S
05-5000 | Metal fabrications & supports | M
07-2000 | Thermal insulation | S
07-8000 | Firestopping | M
08-1000 | Doors, frames & hardware | M
09-2000 | Drywall, patching & painting | S
21-1000 | Fire protection | S
22-1100 | Plumbing labor | L
22-1300 | Domestic water piping & valves | M
22-1400 | Sanitary, vent & storm piping | M
22-3000 | Water heaters & plumbing equipment | M
22-4000 | Plumbing fixtures & trim | M
23-0500 | HVAC / pipefitter labor | L
23-0593 | Testing, adjusting & balancing | S
23-0700 | Pipe & duct insulation | S
23-0900 | Controls hardware | M
23-0910 | Controls programming & BMS | S
23-2300 | Refrigerant, hydronic & condensate piping | M
23-3100 | Ductwork — fab & install | S
23-3700 | Air devices, terminals & dampers | M
23-3800 | Sheet metal & equipment-set labor | L
23-7400 | Packaged rooftop units & accessories | M
23-8100 | Split systems & heat pumps | M
26-0500 | Electrical — power & connections | S
26-5000 | Lighting | M
31-2000 | Earthwork, trenching & backfill | S
32-1000 | Paving & site restoration | S
33-1000 | Site utilities | S
Divisions follow CSI MasterFormat (01 general requirements, 22 plumbing, 23 HVAC, 26 electrical…). Keep a code for contingency and one for sales tax so neither hides inside a material line. Type: L labor · M material · E equipment · S subcontract · O other.
Free template by BuildWorkPro — buildworkpro.com/templates.

## How to Use
How to use the Construction Budget Template
1. | Fill in the project and the original contract value on the Budget sheet. Amber cells are inputs.
2. | Add one row per cost code from the Cost Codes sheet (edit that list to match how you actually buy and track work) with its type: L labor, M material, E equipment, S subcontract, O other.
3. | Enter the original budget for each code — the cost side of your estimate, not the sell price. Overhead and profit are not job costs; contingency and sales tax get their own codes.
4. | When a change order is approved, put its cost (not its price) in Approved changes on the codes it affects, and its price in Approved change orders at the top. Revised budget and revised contract recalculate.
5. | Enter Committed (POs and subcontracts issued) and Actual to date (posted payroll, invoices and receipts) — weekly, from your accounting system. Where you know the cost to finish a code, enter it in Est. to complete; otherwise the projection uses the larger of revised budget, committed and actual.
6. | Read Projected final, Variance (red is over) and % spent by code, and the projected gross profit and margin at the top against the margin you bid.
TIPS FROM THE FIELD
• | Compare % spent to % complete. 74% of the labor budget spent at 60% complete is the earliest warning you will get.
• | Committed is not spent. A PO you issued but have not been invoiced for is still money you owe — include it.
• | Post change-order costs to the codes where the work happens, not to one "changes" line, or you will never know which trades run over.
• | Reconcile revised contract to your latest change order and pay application every month — they should be the same number.
In BuildWorkPro the accepted bid becomes the project’s contract value, approved change orders adjust it automatically, and the Reports module shows bid, project and activity KPIs for any period — exportable to CSV or PDF.
https://buildworkpro.com/features/reports/
Free template by BuildWorkPro — https://buildworkpro.com/templates/. Free to use and share for your own business. Not legal, accounting or engineering advice.