## Pay Application
PAY APPLICATION
G702-style application and certificate for payment
To (Owner / General Contractor):
From (Contractor):
Project:
Application No.:
Period From / To:
Contract Date:
CONTRACTOR'S APPLICATION FOR PAYMENT
1. ORIGINAL CONTRACT SUM | 75000
2. Net change by Change Orders | 0
3. CONTRACT SUM TO DATE (Line 1 + 2)
4. TOTAL COMPLETED & STORED TO DATE (Continuation Sheet, col. G)
5. RETAINAGE
Retainage rate (edit — drives the Continuation Sheet) | 10%
Total retainage withheld (Line 4 × rate)
6. TOTAL EARNED LESS RETAINAGE (Line 4 − 5)
7. LESS PREVIOUS CERTIFICATES FOR PAYMENT | 0
8. CURRENT PAYMENT DUE
9. BALANCE TO FINISH, INCLUDING RETAINAGE (Line 3 − 6)
The undersigned Contractor certifies that the work covered by this application has been completed in accordance with the contract documents.
Contractor signature / date:
Approved by (Owner / GC) / date:
Template by BuildWorkPro — buildworkpro.com. BuildWorkPro generates pay applications like this automatically from your bids and change orders.
Not an official AIA document. "AIA," "G702," and "G703" are trademarks of The American Institute of Architects; this independent template is formatted in the same general style. Confirm with your GC which form they require.

## Continuation Sheet
CONTINUATION SHEET (G703-style schedule of values)
One row per SOV line item. Columns G–J calculate automatically. Overwrite the three sample rows.
Item No. | Description of Work | Scheduled Value | From Previous Applications | This Period | Materials Presently Stored | Total Completed & Stored to Date | % Complete | Balance to Finish | Retainage
1 | Mobilization | 5000 | 5000 | 0 | 0
2 | Rough-in — labor | 42000 | 21000 | 8400 | 0
3 | Fixtures — material | 28000 | 0 | 6000 | 4500
GRAND TOTAL

## How to Use
How to use this template
1. Fill in the project header on the Pay Application sheet (owner/GC, project, application number, billing period).
2. Enter Line 1 (original contract sum) and Line 2 (net approved change orders).
3. On the Continuation Sheet, list your schedule of values — one row per line item. Overwrite the three sample rows.
4. Each billing period, enter This Period and Materials Presently Stored per line. Columns G–J and the summary compute automatically.
5. Set your retainage rate on the Pay Application sheet (amber cell — most contracts are 5% or 10%).
6. After each approved application, move the This Period amounts into From Previous Applications before starting the next one.
Tired of doing this by hand? BuildWorkPro builds the SOV from your accepted bid, locks previous applications, carries everything forward each period, and exports the PDF your GC expects — $79/month flat: https://buildworkpro.com/features/pay-applications/