## RFI Log
RFI Log
One row per request for information. Days open counts from submission until the response date (or today); an overdue response date turns red.
Amber cells are yours to fill in. Everything else calculates.
Project |  |  |  | Open |  | Overdue |  | Avg days to answer
To (A/E / GC) |  |  |  | Answered |  | With cost impact
RFI # | SUBJECT | TO | SUBMITTED | RESPONSE DUE | RESPONDED | DAYS OPEN | STATUS | COST | SCHEDULE | CO REF. | NOTES / RESOLUTION
max days
Free template by BuildWorkPro — buildworkpro.com/templates. An answered RFI that changed scope, cost or time is not finished until its change order number is in the CO ref. column.
Formulas:
DAYS OPEN = IF([SUBMITTED]="","",IF([RESPONDED]="",TODAY()-[SUBMITTED],[RESPONDED]-[SUBMITTED]))

## How to Use
How to use the RFI Log
1. | Enter the project and who RFIs go to at the top. Amber cells are inputs.
2. | Log each RFI the day it is sent: number, subject, to, date submitted and the response-required date (your contract usually sets the turnaround — 7 to 10 days is common).
3. | Days open counts automatically from the submitted date to the responded date, or to today while it is unanswered. The response-due cell turns red once it has passed with no answer.
4. | When the answer arrives, enter the responded date and set the status to Answered. Mark the cost and schedule impact, and if the answer changes the work, put the change order number in CO ref. — an RFI is not closed until its change order is.
5. | The counts at the top show open, answered, overdue and cost-impact RFIs and the average days to answer — the number to bring to the next progress meeting.
TIPS FROM THE FIELD
• | One question per RFI. Bundled RFIs get bundled, unusable answers and cannot be closed independently.
• | Suggest an answer in the RFI itself. A proposed reading gets a faster yes / no than an open question.
• | An RFI response that adds or deletes work is not authorization. Price it on a change order and attach the RFI as backup.
In BuildWorkPro every project carries its documents, comments, change orders, site logs and activity history on one record, so the RFI, the drawing revision it produced and the change order that priced it are all in one place.
https://buildworkpro.com/features/project-management/
Free template by BuildWorkPro — https://buildworkpro.com/templates/. Free to use and share for your own business. Not legal, accounting or engineering advice.