## Schedule of Values
SCHEDULE OF VALUES
Break the contract sum into the line items you will bill against every period. Overwrite the sample rows.
Project:
Contractor:
GC / Owner:
Contract Date:
Contract Sum (target): |  | 75000
Item No. | Description of Work | Scheduled Value | % of Contract | Notes
1 | Mobilization & general conditions | 4500 |  | Keep defensible — GCs scrutinize this line
2 | Rough-in — labor | 24000 |  | Split labor and material when the GC allows
3 | Rough-in — material | 18000
4 | Trim / finish — labor | 12000
5 | Trim / finish — material | 9000
6 | Testing & closeout | 7500 |  | Don't leave closeout too small to bill
TOTAL
Check — total vs contract sum (should be 0.00):
Template by BuildWorkPro — buildworkpro.com. BuildWorkPro builds the SOV from your accepted bid and carries it into every pay application automatically.

## Tips
How to build a schedule of values that gets approved
1. Match the line items to how the work actually phases — you'll bill percentages against each line every month for the life of the job.
2. Keep every value defensible: you should be able to walk the GC through the site and show the work in place for any line you bill.
3. Front-load carefully. Weighting early activities is common; making it obvious invites a rejected application.
4. Don't make closeout lines too small to bother billing — that's how retainage release stalls.
5. The % of Contract column and the check row keep the SOV honest: the total must equal the contract sum exactly.
Full guide: https://buildworkpro.com/blog/schedule-of-values-guide/ · Pay application template: https://buildworkpro.com/templates/aia-g702-g703/